## Activity Log - Ana
Name: | Ana Bergamasco | Project Group (Name/Number): Group 3
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 |  | Spoke with the group outside of session to discuss ideas for the project and prepare the initial project paper | 3 hours | All | Yes
2 | 2024-11-13 | Meeting to define which tasks each member would be responsible for | 1 hour | All | Yes
3 | 2024-11-19 | Meeting with Arthur for feedback on the project | 1 hour | Ana, Chiamaka, Alejandra, Bruna, Lilla | Yes
3 |  | Updated the database and the data_value_check.py | 1 hour |  | Yes
2024-05-04 |  | Added new tables to the database, using LLM to populate the tables | 1 hour |  | Yes
4 | 2024-11-26 | Meeting to check the status of each task | 30 min | All | Yes
4 | 2024-11-26 | Meeting to define features for the front-end part | 1 hour | Ana, Alejandra, Clara | Yes
5 | 2024-12-05 | Meeting to re-assign tasks related to the front-end part | 1 hour | Ana, Alejandra | Yes
5 |  | Development of the code to connect the front-end with the database, to store the data inputed by the user. Database was updated with new tables one more time | 6 hours |  | Yes
5 | 2024-12-08 | Final meeting to check the project paper and presentation slides, and other pending stuff | 45 min | Ana, Clara | Yes
5 | 2024-12-08 | Final meeting to check the front-end part (submission page, dashboard and DB connection) | 40 min | Ana, Alejandra | Yes
5 | 2024-12-08 | Updated the main branch in the repo (cleaned some unused files and merged my branch) | 20 min |  | Yes
1, 2, 3, 4, 5 |  | Took the team leader part and coordinated the development of the project (delegating tasks, scheduling meetings, checking the status of the tasks, talking with instructors), with the help of other team members | 30 hours |  | Yes
Total time:

## Activity Log - Alejandra
Name: | Alejandra Cuadros | Project Group (Name/Number): Group 3
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 |  | Spoke with the group outside of session to discuss ideas for the project and prepare the initial project paper | 3 hours | All | Yes
2 | 2024-11-13 | Meeting to define which tasks each member would be responsible for | 1 hour | All | Yes
3 | 2024-11-19 | Meeting with Arthur for feedback on the project | 1 hour | Ana, Chiamaka, Alejandra, Bruna, Lilla | Yes
3 | 2024-11-28 | First commit of submission page | 120 min | Clara, Alejandra | Yes
3 | 2024-11-22 | Creation of Jira tables, sprint, backlog, activities | 3 hour | Alejandra | Yes
| Daily | Daily update of every task assigned in Jira | 30 | All | Yes
4 | 2024-11-26 | Meeting to check the status of each task | 30 min | All | Yes
4 | 2024-11-26 | Meeting to define features for the front-end part | 1 hour | Ana, Alejandra, Clara | Yes
5 | 2024-12-05 | Meeting to re-assign tasks related to the front-end part | 1 hour | Ana, Alejandra | Yes
4,5 | 29/11/2024 - 09/12/2024 | Development of the front-end code (with streamlit) for the submission page | 45 hour | Alejandra | Yes
4,5 | 29/11/2024 - 09/12/2024 | Development of the front-end code (with streamlit) for the dashboard and back-end to fetch data from the database (SQL queries) to display in the dashboard (analyst view) | 45 hour | Alejandra | Yes
5 | 2024-12-08 | Final meeting to check the front-end part (submission page, dashboard and DB connection) | 40 min | Ana, Alejandra | Yes
Total time:

## Activity Log -Bruna Rocha
Name: | Bruna Rocha | Project Group (Name/Number): InclusiveVenture Lab Project/ Group 3
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 2024-11-08 | Spoke with the group outside of the session to discuss our ideas, define roles, and understand eveyones strenghs and weakness. The initial idea gave by another team member Clara was to do a KYC program, to be used by our sponsor Morgan Stanley, which after a group discussion was decided to use in pair with ALM rules. Explained to the group, what is AML, and what should we be looking for, since some weren`t so familiar with it.At the first week finished the project paper, by answering what we were building, what are the goals of this project, the type of problem it solves, system key features, created the sample architecture diagram, team approach, reasearch data sources, created the README file, git ignore, PEP_AP.py, data_value_check.py, high_risk_countries.txt . As well, initiated by gathering the regulatory reporting requirements, developed the basis of the project such as the initial SQL databasis for data extraction, such as the countries black list and grey list in the European Union,eu_countries_blacklist.sql,PEP_identification.sql ingestion and transformation, API research, legal research, as well a research was done, to understand Morgan Stanley requirements, and presented to the team. | 8h |  | Yes | A bit of desperation striked, due to the amount of work we all had to do, and to be able to find balance with our other responsibilities. But we came through.
2 | 2024-11-11 | We had few group meetings, and some chats as well out of the sessions, to discuss what was missing or not to keep the project going. After, researching I found that OpenSource offers free API access for students, so I enrolled and was able to share it with the team, so we could have a reliable and real data source to use, when checking for PEPs. Did some more integrations regarding data basis, exceptions, errors hadling, lay out what was necessary to be asked to the startups applying to the grant, as well what should contain on their report, did the same for the analysts, did the initial coding to generate the analysts PDF report generate_analyst_report.py. | 10h |  | Yes | This part took me longer, due to my health conditions, and my laptop memory that is close to none.
3 | 2024-12-02 | Created the PPT presentation | 20 min | Myself, Clara and Chiamaka. | Yes
Total time:

## Activity Log - Lilla
.
Name: | Lilla Horváth | Project Group (Name/Number): Group 3
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 |  | Discussed the topic of the project and how it should be done (tasks for the creation process, programming languages to be used, files to be created, softwares to be used (e.g. Jira)) | 2 hours | All | Yes | The tasks were not assigned to individuals yet
1 |  | Created GitHub repository for the project work | 10 minutes | Lilla | Yes
2 |  | Everyone voted on the task(s) they would like to choose; based on this, tasks were assigned. Also discussed who can help with certain tasks | 30 minutes | All | Yes
3 |  | Group discussion with Arthur about project plan | 20 minutes | All | Yes | Arthur gave me some ideas for tests, and a page that explained the differences between unit tests and integration tests
4 |  | Pulled the GitHub repository to my local repository, carefully examined the files, and started working on the tests | altogether approximately 10 hours in 3 days | Lilla | Yes
5 |  | Pulled the changes on the GitHub repository again to check for updates and to run the tests again | 5 hours (approximately) | Lilla | Yes
Total time:

## Activity Log - Chiamaka
Name: | Chiamaka Adinnu | Project Group (Name/Number): Group 3
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 2024-11-04 | Spoke with the group outside of the session to discuss our ideas and prepare the initial project paper for submission. | 1 hour | All | Yes | We agreed on the project idea on this day and fine-tuned it.
2 | 7/11/2024 - 9/11/2024 | Worked on the project paper, wholly answering q1 and q5 and contributing to others except q4. | 1 hour |  | Yes
3 | 2024-11-13 | Had a starter task discussion with team members and agreed on an official meeting day | 30 minutes | All | Yes
3 | 2024-11-13 | Had a meeting with team where we divided our project into tasks and discussed roles | 1 hour | All | Yes
3 | 2024-11-13 | I wrote and submitted our group project description to Addi, who responded positively to our project, giving us the go-ahead to continue. | 30 minutes | None | Yes
4 | 2024-11-19 | Meeting with Arthur for feedback on project | 1 hour | Ana, Alejandra, Bruna, Chiamaka, Lilla | Yes
5 | 2024-11-23 | Informal discussion regarding tasks | 30 minutes | Bruna | Yes
5 | 2024-11-24 | Worked on my part of the project and pushed all files | 7 hours+ |  | Yes
5 | 2024-11-26 | Had a sprint meeting with team to catch up on project's progress and any blockers | 1 hour + | All | Yes
6 | 2024-11-30 | Informal discussion regarding tasks | 30 minutes | Ana | Yes
6 | 2024-11-30 | Worked on project, as discussed with team mate | 1 hour | None | Yes
7 | 2024-12-06 | Discussed with teammate and helped with other pending tasks, including updating the ReadMe and defining requirements file | I hour | Lilla | Yes
7 | 2024-12-07 | Assisted with updating and filling the PPT for our presentation | 45 minutes | Bruna, Chiamaka, and Clara | Yes

## Activity Log - Clara
Name: | Clara Teodoro | Project Group (Name/Number): Group 3
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 |  | Meeting with group |  | All members
2 |  | Meeting with group to decide tasks | 60 min | All members
3 | 2024-11-28 | First commit of submission page | 120 min | Clara, Alejandra | Yes | It wasnt commited to the main branch. File was sent on private to teammember
4 | - | Meeting with group | 30 min | All members
5 | 2024-12-06 | Created draft for project document | 60 min |  | No
5 | 2024-12-07 | Worked on project presentation | 30 min | Clara, Bruna, Chiamaka | No
5 | 2024-12-08 | Data for database insertion file development | 60 min | Clara, Ana | Yes
5 | 2024-12-08 | Changed color text on client dashboard | 20 min |  | Yes
5 | 2024-12-08 | Meeting with Ana about the project document | 30 min
5 | 2024-12-08 | Finalized project document | 120min | Clara | Yes
5 | 2024-12-08 | Worked on presentation | 20min |  | Yes